## Sheet1
Start Date | End Date | Description | Duration (weeks)
2018-12-01 | 2018-12-15 | Hadoop components to support Impala | 2
2018-12-15 | 2018-01-07 | Metadata store | 2
2018-01-07 | 2018-02-01 | File formats | 2
2018-02-01 | 2018-02-07 | Table creation | 1
2018-02-07 | 2018-03-01 | Query coordination | 3
2018-03-01 | 2018-03-21 | Query optimization | 3
2018-03-21 | 2018-04-07 | Monitoring tools | 2
2018-04-07 | 2018-05-01 | Query tuning | 3
Potential guide for Gantt chart: https://www.officetimeline.com/make-gantt-chart/excel#tutorial-auto